# Youth Forum: ECOSOC Youth Forum

Location: New York

2027 date or window: 13–15 April 2027

Date status: official provisional

Website content last verified: 29 August 2026

This document contains the substantive information currently published on the UNYD process guide for this process. Official and primary links are included for checking updates. Planning estimates and recent-cycle precedents are not UN deadlines.

# Process overview

Annual ECOSOC forum on youth participation in the 2030 Agenda and the SDGs. Its programme centres on policy discussion, statements, meetings and follow-up.

Mandate: ECOSOC’s annual forum for youth participation in follow-up and review of the 2030 Agenda and the SDGs.

Main outputs: Policy discussions, national and youth interventions, informal recommendations and side events.

Working structure: Plenaries, thematic sessions, national statements, youth-led events, institutional meetings and peer coordination.

What access depends on: Delegation status determines official participation; event and speaker roles follow separate calls and coordination channels.

Recurring youth relevance: The Forum is designed around youth participation and is especially useful for statements, institutional access, collaboration and initiatives.

## Recurring entry points

Official side-event call — Usually February–March · exact deadline changes. The deadline was 5 March in 2025 and 18 March in 2026. The annual guidelines set eligibility, format and co-sponsor rules; a submitted proposal still requires DESA approval. Status: Annual call; 2027 not yet published.

National statement and speaker route — Before the Forum · coordinated through the national delegation. An official delegation role does not automatically create a speaking slot. The specific national statement or intervention request is handled through the country’s Permanent Mission in New York and the year’s programme arrangements. Status: Delegation-specific.

Ministerial Breakfast — Forum week · documented in 2025 and 2026. A recurring high-level exchange involving ministers, officials and youth representatives. It is strategically useful, but access depends on the cycle’s invitation and delegation arrangements. Status: Recurring recent example; access not automatic.

President’s statement and informal summary — Published after the Forum. These record the Forum’s themes and recommendations and may feed later ECOSOC or HLPF work. They are outputs of the Forum; the ECOSOC Youth Forum does not negotiate a Youth Forum resolution. Status: Recurring official output types.

# UNYD participation

UN Youth Delegates may attend with their national delegation; the precise role and access depend on the national programme and their country’s Permanent Mission in New York.

Common activities include national statements, thematic sessions, institutional meetings, peer coordination and youth-led side events.

The Forum week concentrates meetings with UN entities, Missions and other Youth Delegates that are difficult to arrange remotely.

# Session structure

Before April — Preparation: Theme selection, event proposals and delegation planning

13 April — Opening: Opening plenary and start of the official programme

13–15 April — Forum programme: Thematic sessions, statements, meetings and side events

15 April — Closing and follow-up: Closing session and links to HLPF or later processes

# Preparation and negotiation calendar

The Forum does not normally negotiate one zero draft. Only the documented 2025 side-event and statement sequence is projected here; general advice about choosing priorities or arranging meetings is not placed on the calendar.

Side-event concept development — 2027-02-22 to 2027-03-05: In the documented 2025 case, concrete partner planning and a model concept note were exchanged on 26 February. Status: recent cycle.

DESA side-event proposal deadline — 2027-03-01 to 2027-03-05: The 2025 side-event proposal was submitted on 5 March, matching that cycle’s official call deadline. The 2027 call has not yet been published. Status: recent cycle.

DESA review and approval — 2027-03-06 to 2027-03-17: In the documented 2025 cycle, DESA acknowledged the proposal on 12 March and approved it on 17 March. A submitted proposal should not be treated as accepted before this confirmation. Status: recent cycle.

National delegation briefing and statement request — 2027-03-08 to 2027-03-21: In 2025, the Austrian concept note and speaking request reached the Austrian authorities and Permanent Mission in New York by 21 March. This is a dated precedent, not a universal Forum deadline. Status: recent cycle.

Youth Forum — 2027-04-13 to 2027-04-15: Official provisional forum dates. Status: official.

# Negotiations and policy work

What to follow: The Forum does not normally negotiate a resolution. Its concrete process points are the annual concept note and programme, national statements, the official side-event call, selected institutional meetings and the President’s post-Forum outputs.

## Watch for

The concept note and draft programme: they identify the SDGs under review, session formats, participation arrangements and expected outputs.

The official side-event guidelines. The deadline was 5 March in 2025 and 18 March in 2026; eligibility and co-sponsor requirements are set in each call.

The national-statement and speaker process coordinated through the country’s Permanent Mission in New York, which is separate from applying for a side event.

Recurring but access-dependent moments such as the Ministerial Breakfast. Its 2025 and 2026 editions are documented, but attendance should not be assumed without an invitation or confirmed delegation role.

The ECOSOC President’s statement or informal summary and any “Voices of Youth” input published after the Forum. These are outputs; the ECOSOC Youth Forum does not negotiate a Youth Forum resolution.

Indicative lead time: Monitor the official Forum page from February. A side-event partnership may need to exist before the March call closes; in 2025 the documented proposal was submitted on 5 March, approved on 17 March and shared with the Austrian authorities and Permanent Mission in New York alongside the speaking request on 21 March.

Likely formal route: Use your country’s Permanent Mission in New York for the official delegation and national-statement route. Use the DESA call for side events; under the 2026 rules, an organization without the required status needed an eligible Member State, UN entity or ECOSOC-accredited co-sponsor to submit.

## Negotiation and language resources

Negotiation and language guide: Negotiation process, agreed-language research, resolution structure and text-markup conventions.

UNGA explainer slides · negotiation section: Slides 16–28 show recurring resolutions, drafting roles, the Youth Resolution sequence, agreed language and markup notation.

# Practical timeline

When published · usually February–March — Concept note and draft programme: These identify the SDGs under review, session formats, participation arrangements and expected outputs. The official archive keeps each year’s concept note, programme, statements and summary together.

When the annual call opens — Official side-event guidelines: Check the exact deadline, eligible lead organizer and co-sponsor rule before preparing a proposal. Deadlines changed from 5 March in 2025 to 18 March in 2026, so neither date should be projected as a fixed rule.

After submission — DESA review and approval: Do not treat a submitted side event as accepted. In the documented 2025 case, DESA acknowledged the proposal on 12 March and approved it on 17 March.

About 3–4 weeks before · recent precedent — National statement or speaking request: Send the specific request and supporting concept note through your national authorities and country’s Permanent Mission in New York. The documented Austrian request was sent on 21 March 2025; no universal deadline is claimed.

Forum week — Official programme, statements and selected meetings: Follow confirmed thematic sessions, national statements and approved side events. The Ministerial Breakfast has recurred, but access depends on the cycle’s invitation and delegation arrangements.

After publication — President’s statement and informal summary: Use the official outputs to see which recommendations and themes were carried forward. They inform later ECOSOC and HLPF work but are not a negotiated Forum resolution.

# Examples

Side event — Youth Expertise in Action: Mental Health and Decent Work. A cross-country, youth-partner side event co-developed and co-moderated by UN Youth Delegates during the 2025 Forum.

Meeting — Ministerial Breakfast. A recurring high-value setting for direct exchange among ministers, officials, youth delegates and youth organizations; officially documented in both 2025 and 2026.

Initiative — Launch of the UNYD Coordination Collective. The 2025 Forum provided an in-person anchor for launching a peer coordination structure and connecting current delegates.

# Contacts

UN DESA · IISB: Forum preparation and official side-event proposals — desa-iisb@un.org

Markus Wainde Wane: Former Austrian UN Youth Delegate · Forum participation, side-event process and cross-country UNYD coordination — waindewane@gmail.com

## General UN youth contacts

United Nations Youth Office: General youth-affairs and meaningful-participation enquiries — youthaffairs@un.org

UN DESA · Programme on Youth: UN Youth Delegate Programme and UN youth-system routing — youth@un.org

UNYD Working Group: Peer-run coordination mailbox for current UN Youth Delegates — unyds.workinggroup@gmail.com

# Official and primary sources

ECOSOC Youth Forum 2026

Official Youth Forum side-event guidance

Official Forum archive

2026 Ministerial Breakfast